## Tasks & Hours
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 2 | 4 | 6 | 1
B | Develop marketing strategy |  | 8 | 12 | 16 | 1 |  |  | 1
C | Design brochure | A | 6 | 10 | 14 | 1
D | Develop product prototype
D1 | Requirements analysis | A | 6 | 8 | 10 | 1
D2 | Software design | D1 | 8 | 12 | 16 | 1 | 1 | 1 |  | 1
D3 | System design | D1 | 8 | 12 | 16 | 1 |  |  |  | 1
D4 | Coding | D2, D3 | 20 | 30 | 40 | 1 | 1 | 1 |  | 1
D5 | Write documentation | D4 | 10 | 15 | 20 | 1 |  |  |  | 1
D6 | Unit testing | D4 | 10 | 15 | 20 | 1 | 1 | 1 |  | 1
D7 | System testing | D6 | 12 | 18 | 24 | 1 |  |  |  | 1
D8 | Package deliverables | D5, D7 | 4 | 6 | 8 | 1 |  |  |  | 1
E | Survey potential market | B, C | 10 | 15 | 20 | 1 |  |  | 1
F | Develop pricing plan | D8, E | 6 | 9 | 12 | 1 |  |  | 1
G | Develop implementation plan | A, D8 | 8 | 12 | 16 | 1 |  |  | 1
H | Write client proposal | F, G | 4 | 6 | 8 | 1

## Cost
Assumptions:
1. For any task requiring multiple resources, the hours for that task is split evenly amongst resources with three exceptions (software design, coding, unit testing) | [8 empty] | bestCaseHours | 8304 |  | Salary Cost: | 14604
a. For the software deisgn task, the PM is expected to contribute 2 hours while the remaining hours are split amongst the remaining resources | [8 empty] | expectedHours | 12504 |  | Overhead: | 25%
[9 empty] | worstCaseHours | 16704 |  | Total Cost: | 18500
|  |  |  | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Scenario: | worstCaseHours | <- Toggle
|  |  | Rate per Hour: | 72 | 60 | 60 | 58 | 72 | Scenario Cost: | 16704
task | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Total | Check
Describe product | 2 | 4 | 6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | TRUE
Develop marketing strategy | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Design brochure | 6 | 10 | 14 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | TRUE
Develop product prototype
Requirements analysis | 6 | 8 | 10 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | TRUE
Software design | 8 | 12 | 16 | 1 | 1 | 1 | 0 | 1 | 2 | 4.6667 | 4.6667 | 0 | 4.6667 | 16 | TRUE
System design | 8 | 12 | 16 | 1 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 8 | 16 | TRUE
Coding | 20 | 30 | 40 | 1 | 1 | 1 | 0 | 1 | 2 | 12.6667 | 12.6667 | 0 | 12.6667 | 40 | TRUE
Write documentation | 10 | 15 | 20 | 1 | 0 | 0 | 0 | 1 | 10 | 0 | 0 | 0 | 10 | 20 | TRUE
Unit testing | 10 | 15 | 20 | 1 | 1 | 1 | 0 | 1 | 2 | 6 | 6 | 0 | 6 | 20 | TRUE
System testing | 12 | 18 | 24 | 1 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 12 | 24 | TRUE
Package deliverables | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 4 | 8 | TRUE
Survey potential market | 10 | 15 | 20 | 1 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 10 | 0 | 20 | TRUE
Develop pricing plan | 6 | 9 | 12 | 1 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 6 | 0 | 12 | TRUE
Develop implementation plan | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Write client proposal | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | TRUE
| 122 | 184 | 246 | [5 empty] | 110 | 23.3333 | 23.3333 | 32 | 57.3333
[9 empty] | 7920 | 1400 | 1400 | 1856 | 4128