## Tasks & Hours
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
A | Describe product |  | 2 | 4 | 6 | 1
B | Develop marketing strategy |  | 8 | 12 | 16 | 1 |  |  | 1
C | Design brochure | A | 6 | 10 | 14 | 1
D | Develop product prototype
D1 | Requirements analysis | A | 6 | 8 | 10 | 1
D2 | Software design | D1 | 8 | 12 | 16 | 1 | 1 | 1 |  | 1
D3 | System design | D1 | 8 | 12 | 16 | 1 |  |  |  | 1
D4 | Coding | D2, D3 | 20 | 30 | 40 | 1 | 1 | 1 |  | 1
D5 | Write documentation | D4 | 10 | 15 | 20 | 1 |  |  |  | 1
D6 | Unit testing | D4 | 10 | 15 | 20 | 1 | 1 | 1 |  | 1
D7 | System testing | D6 | 12 | 18 | 24 | 1 |  |  |  | 1
D8 | Package deliverables | D5, D7 | 4 | 6 | 8 | 1 |  |  |  | 1
E | Survey potential market | B, C | 10 | 15 | 20 | 1 |  |  | 1
F | Develop pricing plan | D8, E | 6 | 9 | 12 | 1 |  |  | 1
G | Develop implementation plan | A, D8 | 8 | 12 | 16 | 1 |  |  | 1
H | Write client proposal | F, G | 4 | 6 | 8 | 1
Notes:
1. This tab, 'Tasks & Hours' includes conclusions of research conducted to assess the hours and resources required to complete each task
2. The next tab, 'Costs' includes hourly rates, calculates the pure salary costs required to complete this project, and calculates an overall project estimate cost

## Cost
Assumptions:
1. For any task requiring multiple resources, the hours for that task is split evenly amongst resources with three exceptions (software design, coding, unit testing) | [8 empty] | bestCaseHours | 8304 |  | Salary Cost: | 14604
a. For the software deisgn task, the PM is expected to contribute 2 hours while the remaining hours are split amongst the remaining resources | [8 empty] | expectedHours | 12504 |  | Overhead: | 25%
[9 empty] | worstCaseHours | 16704 |  | Project Cost: | 18500
|  |  |  | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Scenario: | worstCaseHours | <- Toggle
|  |  | Rate per Hour: | 72 | 60 | 60 | 58 | 72 | Scenario Cost: | 16704
task | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Total | Check
Describe product | 2 | 4 | 6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | TRUE
Develop marketing strategy | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Design brochure | 6 | 10 | 14 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | TRUE
Develop product prototype
Requirements analysis | 6 | 8 | 10 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | TRUE
Software design | 8 | 12 | 16 | 1 | 1 | 1 | 0 | 1 | 2 | 4.6667 | 4.6667 | 0 | 4.6667 | 16 | TRUE
System design | 8 | 12 | 16 | 1 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 8 | 16 | TRUE
Coding | 20 | 30 | 40 | 1 | 1 | 1 | 0 | 1 | 2 | 12.6667 | 12.6667 | 0 | 12.6667 | 40 | TRUE
Write documentation | 10 | 15 | 20 | 1 | 0 | 0 | 0 | 1 | 10 | 0 | 0 | 0 | 10 | 20 | TRUE
Unit testing | 10 | 15 | 20 | 1 | 1 | 1 | 0 | 1 | 2 | 6 | 6 | 0 | 6 | 20 | TRUE
System testing | 12 | 18 | 24 | 1 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 12 | 24 | TRUE
Package deliverables | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 4 | 8 | TRUE
Survey potential market | 10 | 15 | 20 | 1 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 10 | 0 | 20 | TRUE
Develop pricing plan | 6 | 9 | 12 | 1 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 6 | 0 | 12 | TRUE
Develop implementation plan | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Write client proposal | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | TRUE
| 122 | 184 | 246 | [5 empty] | 110 | 23.3333 | 23.3333 | 32 | 57.3333
[9 empty] | 7920 | 1400 | 1400 | 1856 | 4128