## Tasks & Hours
taskID | task | predecessorTaskIDs | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | [5 empty] | Best Cost | Expected Cost | Worst Cost
A | Describe product |  | 2 | 4 | 6 | 1 |  |  |  |  | 100% | 0% | 0% | 0% | 0% | 144 | 288 | 432
B | Develop marketing strategy |  | 8 | 12 | 16 | 1 |  |  | 1 |  | 100% | 0% | 0% | 100% | 0% | 1040 | 1560 | 2080
C | Design brochure | A | 6 | 10 | 14 | 1 |  |  |  |  | 100% | 0% | 0% | 0% | 0% | 432 | 720 | 1008
D | Develop product prototype | [9 empty] | 0% | 0% | 0% | 0% | 0% | 0 | 0 | 0
D1 | Requirements analysis | A | 6 | 8 | 10 | 1 |  |  |  |  | 100% | 0% | 0% | 0% | 0% | 432 | 576 | 720
D2 | Software design | D1 | 8 | 12 | 16 | 1 | 1 | 1 |  | 1 | 100% | 100% | 100% | 0% | 100% | 2112 | 3168 | 4224
D3 | System design | D1 | 8 | 12 | 16 | 1 |  |  |  | 1 | 100% | 0% | 0% | 0% | 100% | 1152 | 1728 | 2304
D4 | Coding | D2, D3 | 20 | 30 | 40 | 1 | 1 | 1 |  | 1 | 100% | 100% | 100% | 0% | 100% | 5280 | 7920 | 10560
D5 | Write documentation | D4 | 10 | 15 | 20 | 1 |  |  |  | 1 | 100% | 0% | 0% | 0% | 100% | 1440 | 2160 | 2880
D6 | Unit testing | D4 | 10 | 15 | 20 | 1 | 1 | 1 |  | 1 | 100% | 100% | 100% | 0% | 100% | 2640 | 3960 | 5280
D7 | System testing | D6 | 12 | 18 | 24 | 1 |  |  |  | 1 | 100% | 0% | 0% | 0% | 100% | 1728 | 2592 | 3456
D8 | Package deliverables | D5, D7 | 4 | 6 | 8 | 1 |  |  |  | 1 | 100% | 0% | 0% | 0% | 100% | 576 | 864 | 1152
E | Survey potential market | B, C | 10 | 15 | 20 | 1 |  |  | 1 |  | 100% | 0% | 0% | 100% | 0% | 1300 | 1950 | 2600
F | Develop pricing plan | D8, E | 6 | 9 | 12 | 1 |  |  | 1 |  | 100% | 0% | 0% | 100% | 0% | 780 | 1170 | 1560
G | Develop implementation plan | A, D8 | 8 | 12 | 16 | 1 |  |  | 1 |  | 100% | 0% | 0% | 100% | 0% | 1040 | 1560 | 2080
H | Write client proposal | F, G | 4 | 6 | 8 | 1 |  |  |  |  | 100% | 0% | 0% | 0% | 0% | 288 | 432 | 576
[16 empty] | 20384 | 30648 | 40912
[6 empty] | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer
[5 empty] | Rate per Hour: | 72 | 60 | 60 | 58 | 72
Assumptions:
1. For any task requiring multiple resources, the hours for that task is split evenly amongst resources with three exceptions (software design, coding, unit testing)
a. For the software deisgn task, the PM is expected to contribute 2 hours while the remaining hours are split amongst the remaining resources
[6 empty] | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer

## Cost
Assumptions:
1. For any task requiring multiple resources, the hours for that task is split evenly amongst resources with three exceptions (software design, coding, unit testing) | [8 empty] | bestCaseHours | 8304 |  | Salary Cost: | 14604
a. For the software deisgn task, the PM is expected to contribute 2 hours while the remaining hours are split amongst the remaining resources | [8 empty] | expectedHours | 12504 |  | Overhead: | 25%
[9 empty] | worstCaseHours | 16704 |  | Total Cost: | 18500
|  |  |  | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Scenario: | worstCaseHours | <- Toggle
|  |  | Rate per Hour: | 72 | 60 | 60 | 58 | 72 | Scenario Cost: | 16704
task | bestCaseHours | expectedHours | worstCaseHours | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | projectManager | frontendDeveloper | backendDeveloper | dataScientist | dataEngineer | Total | Check
Describe product | 2 | 4 | 6 | 1 | 0 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 6 | TRUE
Develop marketing strategy | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Design brochure | 6 | 10 | 14 | 1 | 0 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 14 | TRUE
Develop product prototype
Requirements analysis | 6 | 8 | 10 | 1 | 0 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 10 | TRUE
Software design | 8 | 12 | 16 | 1 | 1 | 1 | 0 | 1 | 2 | 4.6667 | 4.6667 | 0 | 4.6667 | 16 | TRUE
System design | 8 | 12 | 16 | 1 | 0 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 8 | 16 | TRUE
Coding | 20 | 30 | 40 | 1 | 1 | 1 | 0 | 1 | 2 | 12.6667 | 12.6667 | 0 | 12.6667 | 40 | TRUE
Write documentation | 10 | 15 | 20 | 1 | 0 | 0 | 0 | 1 | 10 | 0 | 0 | 0 | 10 | 20 | TRUE
Unit testing | 10 | 15 | 20 | 1 | 1 | 1 | 0 | 1 | 2 | 6 | 6 | 0 | 6 | 20 | TRUE
System testing | 12 | 18 | 24 | 1 | 0 | 0 | 0 | 1 | 12 | 0 | 0 | 0 | 12 | 24 | TRUE
Package deliverables | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 1 | 4 | 0 | 0 | 0 | 4 | 8 | TRUE
Survey potential market | 10 | 15 | 20 | 1 | 0 | 0 | 1 | 0 | 10 | 0 | 0 | 10 | 0 | 20 | TRUE
Develop pricing plan | 6 | 9 | 12 | 1 | 0 | 0 | 1 | 0 | 6 | 0 | 0 | 6 | 0 | 12 | TRUE
Develop implementation plan | 8 | 12 | 16 | 1 | 0 | 0 | 1 | 0 | 8 | 0 | 0 | 8 | 0 | 16 | TRUE
Write client proposal | 4 | 6 | 8 | 1 | 0 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 8 | TRUE
| 122 | 184 | 246 | [5 empty] | 110 | 23.3333 | 23.3333 | 32 | 57.3333
[9 empty] | 7920 | 1400 | 1400 | 1856 | 4128